Step ID | Seq | Priority | Workstream | Action | Architecture Reason | Owner | Effort | Prompt | User TODO | Acceptance | Owner Verify | Evidence | Rollback/Teardown | Status | Task Context
W11-001 | 1 | MUST | AI reliability | Implement AI SLI/SLO and error-budget governance for reliability, retrieval quality, grounding, abstention, authorization, privacy, tokens and cost. | Release decisions need measurable user outcomes, including wrong retrieval, leakage and expensive success—not generic availability alone. | Codex (approved source) + Owner (execute/approve) | 3 | W11-001 | SLO-002,ALERT-001 | Definitions and tests cover citation coverage, retrieval relevance, grounded-answer rate, correct abstention, unauthorized retrieval rate, PII leakage rate, tokens and cost per successful query, each with denominator, window, threshold, sample and missing-data behavior. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W11/W11-001.md | Restore prior thresholds only through reviewed policy/runbook change. | Blocked | PLANNED ONLY — W11-001. Implement AI SLI/SLO and error-budget governance for reliability, retrieval quality, grounding, abstention, authorization, privacy, tokens and cost. Definitions and tests cover citation coverage, retrieval relevance, grounded-answer rate, correct abstention, unauthorized retrieval rate, PII leakage rate, tokens and cost per successful query, each with denominator, window, threshold, sample and missing-data behavior. Main Prompt performs repository inspection; Column L/M require separate exact owner-approved manifests. Tracker v1.4.0 may remain open and owner-managed.
W11-002 | 2 | MUST | Chaos engineering | Implement AWS FIS and controlled dependency-chaos framework. | Broader failures must be exercised with exact targets, stop alarms and bounded recovery objectives. | Codex (approved source) + Owner (execute/approve) | 3.5 | W11-002 | FIS-002,RES-002 | Exercises are designed and locally validated; live FIS remains NOT RUN until separately approved. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W11/W11-002.md | Stop exact experiment, restore dependencies/configuration, verify health and reconcile residue. | Blocked | PLANNED ONLY — W11-002: Implement AWS FIS and controlled dependency-chaos framework. Plain-language analogy: a fire drill with marked rooms, observers and an emergency stop—not setting the whole building alight.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W11-003 | 3 | MUST | Disaster recovery | Implement backup, restore, index rebuild and multi-Region DR contracts. | Rollback is not disaster recovery; state, data and indexes need independent recoverability. | Codex (approved source) + Owner (execute/approve) | 4 | W11-003 | DR-001,RPO-001 | Recovery plans bind exact identities and distinguish backup, restore, rebuild, rollback and teardown. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W11/W11-003.md | Abort restore on identity or scope mismatch; preserve original state and recovery evidence. | Blocked | PLANNED ONLY — W11-003: Implement backup, restore, index rebuild and multi-Region DR contracts. Plain-language analogy: rebuilding a library from a verified archive while checking every catalog and access record.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W11-004 | 4 | MUST | Incident operations | Implement incident management, game days, runbooks, failure-proof runners and identity-bound recovery evidence. | Operators need accountable response and proof that recovery achieved the required RTO/RPO, not only a runbook. | Codex (approved source) + Owner (execute/approve) | 4 | W11-004 | INC-001,OPS-001 | Offline and owner-run evidence records exact scenario and identities, approvals, commands/workflows, achieved-versus-target RTO/RPO, integrity/health, cleanup and residual risk; any failed command prevents PASS. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W11/W11-004.md | Disable defective runner/playbook, retain failed evidence and return to last validated runbook. | Blocked | PLANNED ONLY — W11-004. Implement incident management, game days, runbooks, failure-proof runners and identity-bound recovery evidence. Offline and owner-run evidence records exact scenario and identities, approvals, commands/workflows, achieved-versus-target RTO/RPO, integrity/health, cleanup and residual risk; any failed command prevents PASS. Main Prompt performs repository inspection; Column L/M require separate exact owner-approved manifests. Tracker v1.4.0 may remain open and owner-managed.
W11-LEARN-001 | 5 | MUST | Weekly learning | Complete the Week 11 SRE, chaos and DR teach-back. | The owner must distinguish availability, resilience, rollback, restore and disaster recovery. | Codex (approved source) + Owner (execute/approve) | 1 | W11-LEARN-001 | None | Owner explains SLOs, error budgets, chaos safety, RPO/RTO and incident response with five interview answers. | OWNER-CONTROLLED — complete task-specific teach-back after approved content and actual evidence; testing N/A only with reason. | docs/learning/W11-learning-review.md | Revise only through the approved documentation workflow. | Blocked | PLANNED ONLY — W11-LEARN-001: Complete the Week 11 SRE, chaos and DR teach-back. Plain-language analogy: teaching emergency preparedness from alarms through drills, recovery and after-action review.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
Grouped prompt sequence — full Main / Code Edit / Document Writing / Final Approval prompts are in 10 Codex Prompts
Order | Prompt ID | Feature | Purpose | Required Inputs | Expected Outputs | Example Usage
1 | W11-001 | AI reliability | Implement AI SLI/SLO and error-budget governance for reliability, retrieval quality, grounding, abstention, authorization, privacy, tokens and cost. | W7-001-remediation; W10-004 | Definitions and tests cover citation coverage, retrieval relevance, grounded-answer rate, correct abstention, unauthorized retrieval rate, PII leakage rate, tokens and cost per successful query, each with denominator, window, threshold, sample and missing-data behavior. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
2 | W11-002 | Chaos engineering | Implement AWS FIS and controlled dependency-chaos framework. | W7-001-remediation; W11-001 | Exercises are designed and locally validated; live FIS remains NOT RUN until separately approved. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
3 | W11-003 | Disaster recovery | Implement backup, restore, index rebuild and multi-Region DR contracts. | W7-001-remediation; W11-002 | Recovery plans bind exact identities and distinguish backup, restore, rebuild, rollback and teardown. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
4 | W11-004 | Incident operations | Implement incident management, game days, runbooks, failure-proof runners and identity-bound recovery evidence. | W7-001-remediation; W11-003 | Offline and owner-run evidence records exact scenario and identities, approvals, commands/workflows, achieved-versus-target RTO/RPO, integrity/health, cleanup and residual risk; any failed command prevents PASS. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
5 | W11-LEARN-001 | Weekly learning | Complete the Week 11 SRE, chaos and DR teach-back. | W7-001-remediation; W11-004 | Owner explains SLOs, error budgets, chaos safety, RPO/RTO and incident response with five interview answers. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update

## 24 W12 Capstone
Week 12 — Enterprise AI Architect Capstone and Automated Closure
Owner-approved GitHub Actions and HCP Terraform/Terraform Cloud workflows automate deployment, rollback and teardown.
Progress |  |  | Blocked |  |  | Exit gate
0% |  |  | 5 |  |  | All four implementation tasks require their own owner evidence. Deferred W6 P0 gaps do not alone block separately approved source-only Column L; they remain blockers for dependent live/cloud execution and final readiness/closure.
Step ID | Seq | Priority | Workstream | Action | Architecture Reason | Owner | Effort | Prompt | User TODO | Acceptance | Owner Verify | Evidence | Rollback/Teardown | Status | Task Context
W12-001 | 1 | MUST | Automated deployment | Integrate the capstone and automate end-to-end deployment through GitHub Actions and HCP Terraform/Terraform Cloud. | The final operating model must execute approved immutable plans without ad-hoc manual deployment. | Codex (approved source) + Owner (execute/approve) | 4 | W12-001 | GHA-003,TFC-001,PROD-001 | Workflow design preserves explicit owner approval and exact-plan binding; live execution remains separately approved. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W12/W12-001.md | Freeze workflow, preserve run evidence and invoke only the separately approved rollback workflow. | Blocked | PLANNED ONLY — W12-001: Integrate the capstone and automate end-to-end deployment through GitHub Actions and HCP Terraform/Terraform Cloud. Plain-language analogy: a sealed automated assembly line that runs only the signed work order approved by inspectors.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W12-002 | 2 | MUST | Automated recovery | Automate application/infrastructure rollback and validate DR recovery. | Recovery must restore exact known-good identities without manual intervention disguised as automation. | Codex (approved source) + Owner (execute/approve) | 4 | W12-002 | ROLLBACK-002,DR-002 | Application rollback, infrastructure rollback and DR remain separate, identity-bound automated workflows. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W12/W12-002.md | Stop automation, preserve partial state, reconcile read-only and resume only with fresh approval. | Blocked | PLANNED ONLY — W12-002: Automate application/infrastructure rollback and validate DR recovery. Plain-language analogy: three labeled emergency procedures, each with its own key, checklist and verification.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W12-003 | 3 | MUST | Automated teardown | Automate teardown, resource cleanliness and cost closure. | A disposable platform is complete only when approved automation proves native absence and billing closure. | Codex (approved source) + Owner (execute/approve) | 4 | W12-003 | DEST-003,COST-008,KMS-003 | Automated workflow preserves exact approval, ordered teardown, native absence and delayed cost evidence. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W12/W12-003.md | Deletion is not rolled back; stop before uncertain targets and restore only from approved backups where supported. | Blocked | PLANNED ONLY — W12-003: Automate teardown, resource cleanliness and cost closure. Plain-language analogy: closing a facility room by room with an inventory, archive and final utility bills.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W12-004 | 4 | MUST | Governance closure | Prepare the final governance, production-readiness, threat-model and portfolio closure package. | Final readiness must reconcile technical evidence and current attack paths, not infer production status from implementation. | Codex (approved source) + Owner (execute/approve) | 4 | W12-004 | PROD-002,DOC-001 | The package explicitly covers architecture, threat model with accepted/unresolved attack paths, readiness, automated deployment/rollback, DR, teardown, cost, lineage, evaluation/load, dashboards, runbooks and portfolio outputs while preserving every pending or qualified gate. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W12/W12-004.md | Withdraw readiness claim, preserve package, and reopen exact failed or missing gates. | Blocked | PLANNED ONLY — W12-004. Prepare the final governance, production-readiness, threat-model and portfolio closure package. The package explicitly covers architecture, threat model with accepted/unresolved attack paths, readiness, automated deployment/rollback, DR, teardown, cost, lineage, evaluation/load, dashboards, runbooks and portfolio outputs while preserving every pending or qualified gate. Main Prompt performs repository inspection; Column L/M require separate exact owner-approved manifests. Tracker v1.4.0 may remain open and owner-managed.
W12-LEARN-001 | 5 | MUST | Weekly learning | Complete the Week 12 capstone and Principal/Architect teach-back. | The owner must present the entire platform as a governed business, architecture and operations story. | Codex (approved source) + Owner (execute/approve) | 1.5 | W12-LEARN-001 | None | Owner delivers an interview-ready end-to-end narrative and answers architecture, security, SRE, cost and governance follow-ups. | OWNER-CONTROLLED — complete task-specific teach-back after approved content and actual evidence; testing N/A only with reason. | docs/learning/W12-learning-review.md | Revise only through the approved documentation workflow. | Blocked | PLANNED ONLY — W12-LEARN-001: Complete the Week 12 capstone and Principal/Architect teach-back. Plain-language analogy: teaching an audited launch sequence from signed plan through recovery and final site closure.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
Grouped prompt sequence — full Main / Code Edit / Document Writing / Final Approval prompts are in 10 Codex Prompts
Order | Prompt ID | Feature | Purpose | Required Inputs | Expected Outputs | Example Usage
1 | W12-001 | Automated deployment | Integrate the capstone and automate end-to-end deployment through GitHub Actions and HCP Terraform/Terraform Cloud. | W7-001-remediation; W11-004 | Workflow design preserves explicit owner approval and exact-plan binding; live execution remains separately approved. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
2 | W12-002 | Automated recovery | Automate application/infrastructure rollback and validate DR recovery. | W7-001-remediation; W12-001 | Application rollback, infrastructure rollback and DR remain separate, identity-bound automated workflows. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
3 | W12-003 | Automated teardown | Automate teardown, resource cleanliness and cost closure. | W7-001-remediation; W12-002 | Automated workflow preserves exact approval, ordered teardown, native absence and delayed cost evidence. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
4 | W12-004 | Governance closure | Prepare the final governance, production-readiness, threat-model and portfolio closure package. | W7-001-remediation; W12-003 | The package explicitly covers architecture, threat model with accepted/unresolved attack paths, readiness, automated deployment/rollback, DR, teardown, cost, lineage, evaluation/load, dashboards, runbooks and portfolio outputs while preserving every pending or qualified gate. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
5 | W12-LEARN-001 | Weekly learning | Complete the Week 12 capstone and Principal/Architect teach-back. | W7-001-remediation; W12-004 | Owner delivers an interview-ready end-to-end narrative and answers architecture, security, SRE, cost and governance follow-ups. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update