W8-002 | Harden the existing FastAPI inference service. | Production inference should extend the governed API rather than create a duplicate entry point. | reuse authentication/authorization/tenant/correlation controls; typed bounded request/response contracts; deadlines/concurrency/backpressure/rate limits; approved streaming only; safe dependency errors; no endpoint/SDK/prompt/response/secret leakage; safe model/prompt/embedding/retrieval identities; EKS health/readiness/startup alignment; unit/contract/integration/feature/security/load boundaries | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Restore exact known-good API image/configuration and verify health/security gates. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W8-003 | Implement event-driven asynchronous inference and workflow orchestration. | Long-running work needs typed, idempotent, auditable and bounded state transitions. | typed states and terminal outcomes; idempotency/correlation IDs; bounded retries/backoff/DLQ; human approval for sensitive/high-cost actions; bounded fan-out; tenant authorization and quota; resume and compensating actions; audit records; exact failure classification; no unapproved model/provider invocation | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Stop new events, drain or dead-letter exact work, and run approved compensating actions. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W8-004 | Validate autoscaling, load, cost and optional serving-engine decisions. | Serving capacity claims need bounded demand, saturation and cost evidence. | define rate/concurrency/latency/token assumptions; CPU/memory/optional GPU targets; extend existing HPA/PDB; test cold start/scale/saturation/queue/timeouts/dependency failure; cost-per-request guardrails; evaluate Ray Serve only for unmet Python multi-model composition; evaluate Triton only for justified GPU throughput; local/synthetic spike first; record NOT ADOPTED when unjustified; no production claim from synthetic results | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Restore prior scaling/configuration; conditional engines remain disabled unless approved. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W8-LEARN-001 | Complete the Week 8 production-inference teach-back. | The owner must defend serving, API, orchestration, scaling and cost decisions. | Owner teach-back after implementation and evidence review; no runtime action. | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Revise only through the approved documentation workflow. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W9-001 | Implement SageMaker training with PyTorch/Hugging Face and cost-gated PEFT/LoRA. | Owner-managed models need immutable inputs, bounded jobs and safe supply-chain controls. | provider-neutral training contract; model revision/digest/license; CPU/GPU detection and bounded requests; no arbitrary remote code; private artifacts and least privilege; immutable data/code/container/hyperparameters; approval-bound jobs; runtime/storage/budget/network limits; cache integrity; PEFT/LoRA only when approved; failed-job cleanup; no standing production mutation | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Stop exact job, preserve logs/artifacts, clean failed resources and retain known-good model identity. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W9-002 | Implement MLflow experiment, evaluation and lineage workflow. | Experiments must be reproducible without conflating metrics with deployment approval. | run/dataset/code/prompt/model/embedding/retrieval identities; redacted hyperparameters/metrics; privacy-safe golden-set linkage; reproducible lineage and comparison; grounding/citation/abstention/safety/latency/token/cost metrics; no live production data; least privilege/retention/teardown; no raw sensitive prompts/responses; separate experiment result from approval | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Disable tracking integration and retain/export only approved redacted lineage. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W9-003 | Implement SageMaker Model Registry approval and promotion. | Promotion must bind to an exact reviewed package, not a mutable model label. | exact artifact/container/code/evaluation identities; model cards and limitations; approval states and separation of duties; threshold/policy binding; exact package promotion; no mutable tag authority; known-good rollback identity; environment separation; audit/retention/deletion; registry approval does not authorize deployment | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Restore exact approved model package; preserve failed candidate and audit evidence. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W9-004 | Implement secure model CI/CD and supply-chain controls. | Model artifacts require the same immutable, scanned, attested and policy-bound discipline as application images. | GitHub OIDC only; immutable model/container identities; source/license evidence; SBOM where supported; Checkov/Trivy/model/dependency scans; signature/attestation/provenance; OPA promotion gates; exact evaluation binding; separation of build/approve/deploy; no reused failed artifacts; high-vulnerability remediation or explicit risk treatment | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Block candidate, restore exact known-good package/image, and preserve vulnerability/provenance evidence. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W9-LEARN-001 | Complete the Week 9 governed-MLOps teach-back. | The owner must explain training, experiment lineage, registry approval and model supply-chain controls. | Owner teach-back after implementation and evidence review; no runtime action. | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Revise only through the approved documentation workflow. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W10-001 | Implement hybrid retrieval by extending the existing OpenSearch adapter. | Keyword and vector evidence should combine without creating a second RAG stack. | BM25 plus vector retrieval; tenant/classification/ACL filters before results; deterministic fusion and tie-breaking; stable result identities; query normalization; bounded top-k and timeouts; citation-compatible evidence; Qdrant/OpenSearch contract preservation; safe abstention on insufficient evidence | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Disable hybrid mode and restore the exact approved retrieval configuration/index identity. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W10-002 | Implement reranking, backend parity and retrieval load/cost proof. | Reranking is useful only when it measurably improves relevance within latency and cost bounds. | provider-neutral reranker interface; approved model identity/license; bounded candidate and top-N sizes; timeouts and safe fallback; Qdrant/OpenSearch parity fixtures; tenant isolation; relevance/latency/cost comparison; load and dependency failure; record NOT ADOPTED if benefit is insufficient | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Disable reranker, restore prior retrieval configuration, and retain comparison evidence. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W10-003 | Implement RAG evaluation, safety regression and version governance. | Production claims require a live privacy-safe golden set and immutable evaluation identities. | versioned synthetic live golden set; retrieval/groundedness/citation/abstention/safety metrics; deterministic tolerances; prompt/model/embedding/retrieval/index identities; security and tenant regressions; token/latency/cost bounds; candidate versus known-good comparison; owner-approved thresholds; failed reports retained; no PASS from plan or local-only evidence | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Restore exact known-good RAG configuration and block failed candidate identities. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W10-004 | Implement AI observability, drift, resilience and cost operations. | Model and RAG behavior must be diagnosable without retaining sensitive payloads. | extend existing OTel path; stable low-cardinality model/RAG dimensions; request/test/provider correlation; quality/latency/token/cost telemetry; data/retrieval/model drift signals; privacy-safe synthetic transcript policy; Bedrock logging disabled by default; delivery success/failure alarms; bounded retention; dependency resilience dashboards/runbooks | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Disable new exporters/logging, preserve safe evidence and retain existing telemetry path. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W10-LEARN-001 | Complete the Week 10 advanced-RAG and LLMOps teach-back. | The owner must explain hybrid retrieval, reranking, evaluation and privacy-safe operations. | Owner teach-back after implementation and evidence review; no runtime action. | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Revise only through the approved documentation workflow. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W11-001 | Implement AI SLI/SLO and error-budget governance. | Release decisions need user-centered reliability and quality objectives backed by evaluable telemetry. | availability/latency/retrieval/grounding/citation/abstention/safety SLIs; stable metric dimensions; minimum population and window; error-budget policy; multi-window burn alerts; release freeze/degraded-mode rules; primary/backup ownership; telemetry readiness before rollback/chaos; no production claim from short synthetic windows | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Restore prior thresholds only through reviewed policy/runbook change. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W11-002 | Implement AWS FIS and controlled dependency-chaos framework. | Broader failures must be exercised with exact targets, stop alarms and bounded recovery objectives. | node drain/loss and AZ-aware scheduling; OpenSearch degradation; Bedrock throttle/timeout; telemetry outage; controlled load; exact tag/identity targets; stop alarms and abort authority; per-scenario approval; no unbounded blast radius; recovery and residual checks | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Stop exact experiment, restore dependencies/configuration, verify health and reconcile residue. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W11-003 | Implement backup, restore, index rebuild and multi-Region DR contracts. | Rollback is not disaster recovery; state, data and indexes need independent recoverability. | approved RPO/RTO; bootstrap/platform state recovery snapshots; S3/OpenSearch/model/evidence backup scope; index rebuild from immutable sources; cluster/workspace recovery; multi-Region decision and residency; exact encryption/IAM identities; restore validation and tenant isolation; cost and teardown; no production DR claim without exercise | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Abort restore on identity or scope mismatch; preserve original state and recovery evidence. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W11-004 | Implement incident management, game day, runbooks and failure-proof runners. | Operators need accountable response and automation that cannot emit PASS after command failure. | primary/backup on-call and escalation; incident severity/roles/timeline; game-day matrix; model/RAG/data/platform runbooks; Windows PowerShell 5.1 and PowerShell 7 tests; authoritative native-command runner; stdout/stderr/exit/tool-version/elapsed capture; zero/one/many and optional-field fixtures; timeouts/progress/rejoin; failed command can never emit PASS | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Disable defective runner/playbook, retain failed evidence and return to last validated runbook. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W11-LEARN-001 | Complete the Week 11 SRE, chaos and DR teach-back. | The owner must distinguish availability, resilience, rollback, restore and disaster recovery. | Owner teach-back after implementation and evidence review; no runtime action. | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Revise only through the approved documentation workflow. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W12-001 | Integrate the capstone and automate end-to-end deployment through GitHub Actions and HCP Terraform/Terraform Cloud. | The final operating model must execute approved immutable plans without ad-hoc manual deployment. | GitHub OIDC and protected environments; HCP Terraform/Terraform Cloud workspaces/policy sets; exact source/state/plan/artifact identities; build/scan/attest/evaluate/register; saved-plan and owner approval binding; automated apply after approval; health/security/evaluation/SLO verification; no static credentials; no manual console/CLI deployment; Codex has no autonomous mutation authority | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Freeze workflow, preserve run evidence and invoke only the separately approved rollback workflow. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W12-002 | Automate application/infrastructure rollback and validate DR recovery. | Recovery must restore exact known-good identities without manual intervention disguised as automation. | separate application and infrastructure approvals; exact known-good image/model/config; health/readiness/traffic verification; failed-release evidence; telemetry readiness; separately reviewed Terraform rollback plan; state lineage/serial binding; reject stale/substituted plans; shared/service-linked exclusions; RPO/RTO restore/index rebuild verification; stop on incomplete authority/evidence | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Stop automation, preserve partial state, reconcile read-only and resume only with fresh approval. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W12-003 | Automate teardown, resource cleanliness and cost closure. | A disposable platform is complete only when approved automation proves native absence and billing closure. | workload/data/feature/index/model/ECR cleanup; platform destroy then bootstrap last; shared/service-linked exclusions; native absence verification; KMS residual/deletion checks; 24/48/72-hour billing checks; USD 20 or latest approved ceiling; retained-resource inventory; evidence archive before deletion; stop on uncertain ownership; no unapproved deletion or manual teardown | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Deletion is not rolled back; stop before uncertain targets and restore only from approved backups where supported. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W12-004 | Prepare final governance, production-readiness and portfolio closure package. | Production readiness is an evidence decision, not a label inferred from implementation. | complete current/superseded evidence index and hashes; architecture and Terraform/CI traceability; observability/security/model-supply-chain results; SLO/chaos/DR/rollback/teardown/cost evidence; runbooks and game-day records; known limitations/accepted risks/NOT RUN/INDETERMINATE; Column M documentation; Column N reviewer decision/timestamp; owner-only tracker update; interview-ready narrative and portfolio index; remain NOT ESTABLISHED on missing/stale/waived/failed evidence | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Withdraw readiness claim, preserve package, and reopen exact failed or missing gates. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review
W12-LEARN-001 | Complete the Week 12 capstone and Principal/Architect teach-back. | The owner must present the entire platform as a governed business, architecture and operations story. | Owner teach-back only after applicable implementation, evidence and approval; no runtime action. | Task-specific controls must be explained after implementation without secrets or unsupported claims. | Explain selected option, alternatives, trade-offs and revisit trigger. | Owner evidence only; plan and prompt are NOT RUN. | Revise only through the approved documentation workflow. | BLOCKED — IMPLEMENTATION NOT COMPLETE | PENDING — complete only after implementation and final evidence review

## 19 W7 Data Platform
Week 7 — Governed Enterprise Data Platform
Governed source, quality, privacy and feature-management decisions extend the existing RAG data path.
Progress |  |  | Blocked |  |  | Exit gate
0% |  |  | 5 |  |  | All four implementation tasks require their own owner evidence. Deferred W6 P0 gaps do not alone block separately approved source-only Column L; they remain blockers for dependent live/cloud execution and final readiness/closure.
Step ID | Seq | Priority | Workstream | Action | Architecture Reason | Owner | Effort | Prompt | User TODO | Acceptance | Owner Verify | Evidence | Rollback/Teardown | Status | Task Context
W7-001-remediation | 0 | MUST | W6 closure remediation | Close or formally disposition W6 lifecycle, evidence and repeatability gaps before new capability. | New platform capability must not build on unresolved lifecycle, billing, KMS, evidence or automation defects. | Codex (approved source) + Owner (execute/approve) | 4 | W7-001-remediation | W6-CLOSE-001,COST-002,KMS-002 | Every P0 gap is closed with owner evidence or explicitly remains blocking; P1/P2 work is mapped with no false PASS. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W7/W7-001-remediation.md | Append-only remediation records; preserve every W6 historical classification and hash. | Not Started | PLANNED ONLY — W7-001-remediation: Close or formally disposition W6 lifecycle, evidence and repeatability gaps before new capability. Plain-language analogy: Codex must supply one grounded in the actual implementation. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W7-001 | 2 | MUST | Governed data foundation | Implement secure data lake, catalog, lineage and ingestion foundation. | Documents need deterministic identity, ownership, validation and quarantine before embedding or indexing. | Codex (approved source) + Owner (execute/approve) | 4 | W7-001 | DATA-004,RES-001 | Plans, contracts and local security/state-transition/idempotency tests prove no invalid document reaches embedding/indexing. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W7/W7-001.md | Disable ingestion handoff; retain source/evidence; remove only exact new sandbox resources after approved teardown. | Blocked | PLANNED ONLY — W7-001: Implement secure data lake, catalog, lineage and ingestion foundation. Plain-language analogy: an airport baggage system that labels, screens and quarantines every item before loading.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W7-002 | 3 | MUST | Data processing and quality | Implement W7-002 transformation and quality: preserve the completed W7-001 foundation, map validated/curated logical states into the approved processed workflow, decide actual Great Expectations versus a compatible contract, and implement Glue/Spark processing, thresholds, drift, quarantine and safe replay. | W7-001 already owns intake, physical zones, lineage and handoff. W7-002 must own transformation and quality without duplicating that foundation or silently changing zone semantics. | Codex (approved source) + Owner (execute/approve) | 4 | W7-002 | DATA-005,DQ-001 | Repository-inspected contracts prove the ownership split, approved zone-state mapping, explicit Great Expectations decision, owner-approved thresholds and deterministic duplicate/corrupt/partial/retry/tenant/PII/drift/replay outcomes. Results remain NOT RUN until owner testing. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W7/W7-002.md | Stop replay, preserve checkpoints and quarantine, and restore the last approved processing contract. | Blocked | PLANNED ONLY — W7-002. Implement W7-002 transformation and quality: preserve the completed W7-001 foundation, map validated/curated logical states into the approved processed workflow, decide actual Great Expectations versus a compatible contract, and implement Glue/Spark processing, thresholds, drift, quarantine and safe replay. Repository-inspected contracts prove the ownership split, approved zone-state mapping, explicit Great Expectations decision, owner-approved thresholds and deterministic duplicate/corrupt/partial/retry/tenant/PII/drift/replay outcomes. Results remain NOT RUN until owner testing. Main Prompt performs repository inspection; Column L/M require separate exact owner-approved manifests. Tracker v1.4.0 may remain open and owner-managed.
W7-003 | 4 | MUST | Privacy and lifecycle | Implement Macie/Presidio privacy, retention, deletion and re-index controls. | Sensitive data must be governed before embedding and deletions must propagate exactly across source and index layers. | Codex (approved source) + Owner (execute/approve) | 3.5 | W7-003 | PRIV-002,RET-002,DEST-002 | Privacy and lifecycle contracts fail closed and identify exact owner approval for every destructive operation. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W7/W7-003.md | Revoke release, quarantine affected versions, preserve evidence and restore last approved index manifest. | Blocked | PLANNED ONLY — W7-003: Implement Macie/Presidio privacy, retention, deletion and re-index controls. Plain-language analogy: a records office that tracks every copy and destroys only authorized records with a witnessed chain of custody.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W7-004 | 5 | MUST | Feature management decision | Decide and conditionally implement the smallest justified feature-management workflow. | A document-RAG platform should not operate unused feature-store infrastructure. | Codex (approved source) + Owner (execute/approve) | 2.5 | W7-004 | FEATURE-001,COST-003 | Owner-approved ADR records adoption or governed non-adoption; no live feature store is claimed without evidence. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W7/W7-004.md | Disable conditional integration and remove only exact feature resources under a reviewed teardown plan. | Blocked | PLANNED ONLY — W7-004: Decide and conditionally implement the smallest justified feature-management workflow. Plain-language analogy: choosing whether a shared pantry is justified before building and stocking one.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W7-LEARN-001 | 6 | MUST | Weekly learning | Complete the Week 7 governed-data-platform teach-back. | The owner must explain lineage, quality, privacy, replay and feature-management trade-offs. | Codex (approved source) + Owner (execute/approve) | 1 | W7-LEARN-001 | None | Owner explains the Week 7 business story, data/control flow, failure boundaries and five interview answers. | OWNER-CONTROLLED — complete task-specific teach-back after approved content and actual evidence; testing N/A only with reason. | docs/learning/W7-learning-review.md | Revise only through the approved documentation workflow. | Blocked | PLANNED ONLY — W7-LEARN-001: Complete the Week 7 governed-data-platform teach-back. Plain-language analogy: teaching how a secure records supply chain screens, labels and tracks every document.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
Grouped prompt sequence — full Main / Code Edit / Document Writing / Final Approval prompts are in 10 Codex Prompts
Order | Prompt ID | Feature | Purpose | Required Inputs | Expected Outputs | Example Usage
1 | W7-001-remediation | W6 closure remediation | Close or formally disposition W6 lifecycle, evidence and repeatability gaps before new capability. | W6-004 P0/P1/P2 register | Every P0 gap is closed with owner evidence or explicitly remains blocking; P1/P2 work is mapped with no false PASS. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
2 | W7-001 | Governed data foundation | Implement secure data lake, catalog, lineage and ingestion foundation. | W7-001-remediation | Plans, contracts and local security/state-transition/idempotency tests prove no invalid document reaches embedding/indexing. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
3 | W7-002 | Data processing and quality | Implement W7-002 transformation and quality: preserve the completed W7-001 foundation, map validated/curated logical states into the approved processed workflow, decide actual Great Expectations versus a compatible contract, and implement Glue/Spark processing, thresholds, drift, quarantine and safe replay. | W7-001-remediation; W7-001 | Repository-inspected contracts prove the ownership split, approved zone-state mapping, explicit Great Expectations decision, owner-approved thresholds and deterministic duplicate/corrupt/partial/retry/tenant/PII/drift/replay outcomes. Results remain NOT RUN until owner testing. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
4 | W7-003 | Privacy and lifecycle | Implement Macie/Presidio privacy, retention, deletion and re-index controls. | W7-001-remediation; W7-002 | Privacy and lifecycle contracts fail closed and identify exact owner approval for every destructive operation. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
5 | W7-004 | Feature management decision | Decide and conditionally implement the smallest justified feature-management workflow. | W7-001-remediation; W7-003 | Owner-approved ADR records adoption or governed non-adoption; no live feature store is claimed without evidence. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
6 | W7-LEARN-001 | Weekly learning | Complete the Week 7 governed-data-platform teach-back. | W7-001-remediation; W7-004 | Owner explains the Week 7 business story, data/control flow, failure boundaries and five interview answers. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update

## 20 W8 Prod Inference
Week 8 — Production Inference and Orchestration
Production inference extends the existing FastAPI, Bedrock, EKS and workflow boundaries without duplication.
Progress |  |  | Blocked |  |  | Exit gate
0% |  |  | 5 |  |  | All four implementation tasks require their own owner evidence. Deferred W6 P0 gaps do not alone block separately approved source-only Column L; they remain blockers for dependent live/cloud execution and final readiness/closure.
Step ID | Seq | Priority | Workstream | Action | Architecture Reason | Owner | Effort | Prompt | User TODO | Acceptance | Owner Verify | Evidence | Rollback/Teardown | Status | Task Context
W8-001 | 1 | MUST | Serving architecture | Define the production serving ADR: Bedrock for foundation models; SageMaker real-time endpoints as the AWS-first default for approved custom/fine-tuned managed hosting; EKS, Ray Serve or Triton only with evidenced justification. | Each model class needs a least-privilege, reversible topology without provisioning every serving engine. | Codex (approved source) + Owner (execute/approve) | 2.5 | W8-001 | SERVE-001,AWS-003 | The ADR records model/artifact criteria, managed-hosting default, conditional alternatives, private access, scaling, cost and teardown; design evidence does not claim provisioning. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W8/W8-001.md | Supersede only through a reviewed serving ADR; no resource exists from design. | Blocked | PLANNED ONLY — W8-001. Define the production serving ADR: Bedrock for foundation models; SageMaker real-time endpoints as the AWS-first default for approved custom/fine-tuned managed hosting; EKS, Ray Serve or Triton only with evidenced justification. The ADR records model/artifact criteria, managed-hosting default, conditional alternatives, private access, scaling, cost and teardown; design evidence does not claim provisioning. Main Prompt performs repository inspection; Column L/M require separate exact owner-approved manifests. Tracker v1.4.0 may remain open and owner-managed.
W8-002 | 2 | MUST | Inference API | Harden the existing FastAPI inference service with streaming, limits, timeouts, backpressure and graceful shutdown. | Production inference must preserve the governed API while draining safely and refusing new work during termination. | Codex (approved source) + Owner (execute/approve) | 4 | W8-002 | IDENT-001,SERVE-002 | Tests cover readiness withdrawal, connection draining, zero new work after shutdown, bounded in-flight completion/cancellation, streaming disconnect, dependency closure and termination deadline without a duplicate API path. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W8/W8-002.md | Restore exact known-good API image/configuration and verify health/security gates. | Blocked | PLANNED ONLY — W8-002. Harden the existing FastAPI inference service with streaming, limits, timeouts, backpressure and graceful shutdown. Tests cover readiness withdrawal, connection draining, zero new work after shutdown, bounded in-flight completion/cancellation, streaming disconnect, dependency closure and termination deadline without a duplicate API path. Main Prompt performs repository inspection; Column L/M require separate exact owner-approved manifests. Tracker v1.4.0 may remain open and owner-managed.
W8-003 | 3 | MUST | Async orchestration | Implement EventBridge/Step Functions-compatible asynchronous inference, ingestion and training orchestration. | Long-running inference, ingestion and training require typed, auditable states and explicit failure routing. | Codex (approved source) + Owner (execute/approve) | 3.5 | W8-003 | ORCH-001,COST-004 | Contracts and tests cover approval, retry/backoff, timeout, terminal failure routing, DLQ, compensation, resume and idempotent redelivery across inference, ingestion and training workflows. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W8/W8-003.md | Stop new events, drain or dead-letter exact work, and run approved compensating actions. | Blocked | PLANNED ONLY — W8-003. Implement EventBridge/Step Functions-compatible asynchronous inference, ingestion and training orchestration. Contracts and tests cover approval, retry/backoff, timeout, terminal failure routing, DLQ, compensation, resume and idempotent redelivery across inference, ingestion and training workflows. Main Prompt performs repository inspection; Column L/M require separate exact owner-approved manifests. Tracker v1.4.0 may remain open and owner-managed.
W8-004 | 4 | MUST | Capacity and cost | Validate load, latency, saturation, autoscaling and cost per successful request; include HPA/PDB and Karpenter when EKS serving is selected, or SageMaker autoscaling when a custom endpoint is selected. | Capacity claims need workload evidence and safe node/workload scaling, not HPA-only coverage. | Codex (approved source) + Owner (execute/approve) | 3 | W8-004 | CAP-001,COST-005 | Owner-run tests cover scale-out/in, Karpenter provisioning/consolidation/disruption, cold start, saturation, queue/timeouts and cost per successful request for the selected runtime; Ray Serve/Triton remain conditional. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W8/W8-004.md | Restore prior scaling/configuration; conditional engines remain disabled unless approved. | Blocked | PLANNED ONLY — W8-004. Validate load, latency, saturation, autoscaling and cost per successful request; include HPA/PDB and Karpenter when EKS serving is selected, or SageMaker autoscaling when a custom endpoint is selected. Owner-run tests cover scale-out/in, Karpenter provisioning/consolidation/disruption, cold start, saturation, queue/timeouts and cost per successful request for the selected runtime; Ray Serve/Triton remain conditional. Main Prompt performs repository inspection; Column L/M require separate exact owner-approved manifests. Tracker v1.4.0 may remain open and owner-managed.
W8-LEARN-001 | 5 | MUST | Weekly learning | Complete the Week 8 production-inference teach-back. | The owner must defend serving, API, orchestration, scaling and cost decisions. | Codex (approved source) + Owner (execute/approve) | 1 | W8-LEARN-001 | None | Owner explains the serving decision, safe request path, overload behavior and five interview answers. | OWNER-CONTROLLED — complete task-specific teach-back after approved content and actual evidence; testing N/A only with reason. | docs/learning/W8-learning-review.md | Revise only through the approved documentation workflow. | Blocked | PLANNED ONLY — W8-LEARN-001: Complete the Week 8 production-inference teach-back. Plain-language analogy: teaching how a secure restaurant handles dine-in, queued orders and kitchen capacity.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
Grouped prompt sequence — full Main / Code Edit / Document Writing / Final Approval prompts are in 10 Codex Prompts
Order | Prompt ID | Feature | Purpose | Required Inputs | Expected Outputs | Example Usage
1 | W8-001 | Serving architecture | Define the production serving ADR: Bedrock for foundation models; SageMaker real-time endpoints as the AWS-first default for approved custom/fine-tuned managed hosting; EKS, Ray Serve or Triton only with evidenced justification. | W7-001-remediation; W7-004 | The ADR records model/artifact criteria, managed-hosting default, conditional alternatives, private access, scaling, cost and teardown; design evidence does not claim provisioning. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
2 | W8-002 | Inference API | Harden the existing FastAPI inference service with streaming, limits, timeouts, backpressure and graceful shutdown. | W7-001-remediation; W8-001 | Tests cover readiness withdrawal, connection draining, zero new work after shutdown, bounded in-flight completion/cancellation, streaming disconnect, dependency closure and termination deadline without a duplicate API path. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
3 | W8-003 | Async orchestration | Implement EventBridge/Step Functions-compatible asynchronous inference, ingestion and training orchestration. | W7-001-remediation; W8-002 | Contracts and tests cover approval, retry/backoff, timeout, terminal failure routing, DLQ, compensation, resume and idempotent redelivery across inference, ingestion and training workflows. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
4 | W8-004 | Capacity and cost | Validate load, latency, saturation, autoscaling and cost per successful request; include HPA/PDB and Karpenter when EKS serving is selected, or SageMaker autoscaling when a custom endpoint is selected. | W7-001-remediation; W8-003 | Owner-run tests cover scale-out/in, Karpenter provisioning/consolidation/disruption, cold start, saturation, queue/timeouts and cost per successful request for the selected runtime; Ray Serve/Triton remain conditional. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
5 | W8-LEARN-001 | Weekly learning | Complete the Week 8 production-inference teach-back. | W7-001-remediation; W8-004 | Owner explains the serving decision, safe request path, overload behavior and five interview answers. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update

## 21 W9 MLOps
Week 9 — Governed MLOps and Secure Model Supply Chain
Training, experiment lineage, model approval and promotion extend existing DevSecOps controls.
Progress |  |  | Blocked |  |  | Exit gate
0% |  |  | 5 |  |  | All four implementation tasks require their own owner evidence. Deferred W6 P0 gaps do not alone block separately approved source-only Column L; they remain blockers for dependent live/cloud execution and final readiness/closure.
Step ID | Seq | Priority | Workstream | Action | Architecture Reason | Owner | Effort | Prompt | User TODO | Acceptance | Owner Verify | Evidence | Rollback/Teardown | Status | Task Context
W9-001 | 1 | MUST | Governed training | Implement SageMaker training with PyTorch/Hugging Face and cost-gated PEFT/LoRA. | Owner-managed models need immutable inputs, bounded jobs and safe supply-chain controls. | Codex (approved source) + Owner (execute/approve) | 4 | W9-001 | TRAIN-001,COST-006 | Training contracts, local tests, budgets and teardown are reviewable; no job is submitted without separate approval. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W9/W9-001.md | Stop exact job, preserve logs/artifacts, clean failed resources and retain known-good model identity. | Blocked | PLANNED ONLY — W9-001: Implement SageMaker training with PyTorch/Hugging Face and cost-gated PEFT/LoRA. Plain-language analogy: a controlled laboratory experiment where every ingredient, instrument and budget is logged before starting.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W9-002 | 2 | MUST | Experiment lineage | Implement MLflow experiment, evaluation and lineage workflow. | Experiments must be reproducible without conflating metrics with deployment approval. | Codex (approved source) + Owner (execute/approve) | 3 | W9-002 | MLFLOW-001,RET-003 | A bounded local or approved managed MLflow pattern records privacy-safe reproducible lineage. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W9/W9-002.md | Disable tracking integration and retain/export only approved redacted lineage. | Blocked | PLANNED ONLY — W9-002: Implement MLflow experiment, evaluation and lineage workflow. Plain-language analogy: a lab notebook that records exact ingredients and results but cannot authorize factory release.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W9-003 | 3 | MUST | Model registry | Implement SageMaker Model Registry approval and promotion. | Promotion must bind to an exact reviewed package, not a mutable model label. | Codex (approved source) + Owner (execute/approve) | 3 | W9-003 | REGISTRY-001 | Registry contracts and promotion/rollback identities fail closed on substitution or missing evidence. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W9/W9-003.md | Restore exact approved model package; preserve failed candidate and audit evidence. | Blocked | PLANNED ONLY — W9-003: Implement SageMaker Model Registry approval and promotion. Plain-language analogy: a controlled release vault where a signed serial-numbered item can move stages but not deploy itself.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W9-004 | 4 | MUST | Model supply chain | Implement secure model CI/CD and supply-chain controls. | Model artifacts require the same immutable, scanned, attested and policy-bound discipline as application images. | Codex (approved source) + Owner (execute/approve) | 3.5 | W9-004 | SUPPLY-002,GHA-002 | CI/CD design rejects unscanned, mutable, unlicensed, unattested or unapproved model artifacts. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W9/W9-004.md | Block candidate, restore exact known-good package/image, and preserve vulnerability/provenance evidence. | Blocked | PLANNED ONLY — W9-004: Implement secure model CI/CD and supply-chain controls. Plain-language analogy: an airport security chain that verifies identity, contents, seals and authorization before transfer.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W9-LEARN-001 | 5 | MUST | Weekly learning | Complete the Week 9 governed-MLOps teach-back. | The owner must explain training, experiment lineage, registry approval and model supply-chain controls. | Codex (approved source) + Owner (execute/approve) | 1 | W9-LEARN-001 | None | Owner explains exact model identity, separation of duties, promotion and rollback with five interview answers. | OWNER-CONTROLLED — complete task-specific teach-back after approved content and actual evidence; testing N/A only with reason. | docs/learning/W9-learning-review.md | Revise only through the approved documentation workflow. | Blocked | PLANNED ONLY — W9-LEARN-001: Complete the Week 9 governed-MLOps teach-back. Plain-language analogy: teaching a pharmaceutical chain from controlled experiment to approved sealed batch.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
Grouped prompt sequence — full Main / Code Edit / Document Writing / Final Approval prompts are in 10 Codex Prompts
Order | Prompt ID | Feature | Purpose | Required Inputs | Expected Outputs | Example Usage
1 | W9-001 | Governed training | Implement SageMaker training with PyTorch/Hugging Face and cost-gated PEFT/LoRA. | W7-001-remediation; W8-004 | Training contracts, local tests, budgets and teardown are reviewable; no job is submitted without separate approval. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
2 | W9-002 | Experiment lineage | Implement MLflow experiment, evaluation and lineage workflow. | W7-001-remediation; W9-001 | A bounded local or approved managed MLflow pattern records privacy-safe reproducible lineage. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
3 | W9-003 | Model registry | Implement SageMaker Model Registry approval and promotion. | W7-001-remediation; W9-002 | Registry contracts and promotion/rollback identities fail closed on substitution or missing evidence. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
4 | W9-004 | Model supply chain | Implement secure model CI/CD and supply-chain controls. | W7-001-remediation; W9-003 | CI/CD design rejects unscanned, mutable, unlicensed, unattested or unapproved model artifacts. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
5 | W9-LEARN-001 | Weekly learning | Complete the Week 9 governed-MLOps teach-back. | W7-001-remediation; W9-004 | Owner explains exact model identity, separation of duties, promotion and rollback with five interview answers. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update

## 22 W10 Advanced RAG
Week 10 — Advanced RAG and LLMOps
Hybrid retrieval, reranking, evaluation and AI operations extend the existing cited-RAG path.
Progress |  |  | Blocked |  |  | Exit gate
0% |  |  | 5 |  |  | All four implementation tasks require their own owner evidence. Deferred W6 P0 gaps do not alone block separately approved source-only Column L; they remain blockers for dependent live/cloud execution and final readiness/closure.
Step ID | Seq | Priority | Workstream | Action | Architecture Reason | Owner | Effort | Prompt | User TODO | Acceptance | Owner Verify | Evidence | Rollback/Teardown | Status | Task Context
W10-001 | 1 | MUST | Hybrid retrieval | Implement hybrid retrieval by extending the existing OpenSearch adapter. | Keyword and vector evidence should combine without creating a second RAG stack. | Codex (approved source) + Owner (execute/approve) | 3.5 | W10-001 | RAG-002 | Hybrid retrieval contract preserves authorization, citations and deterministic normalized results. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W10/W10-001.md | Disable hybrid mode and restore the exact approved retrieval configuration/index identity. | Blocked | PLANNED ONLY — W10-001: Implement hybrid retrieval by extending the existing OpenSearch adapter. Plain-language analogy: combining two ranked library catalogs while rechecking every book's access label.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W10-002 | 2 | MUST | Reranking and parity | Implement reranking, backend parity and retrieval load/cost proof. | Reranking is useful only when it measurably improves relevance within latency and cost bounds. | Codex (approved source) + Owner (execute/approve) | 3 | W10-002 | RERANK-001,COST-007 | Measured criteria govern reranker adoption; parity and authorization regressions fail closed. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W10/W10-002.md | Disable reranker, restore prior retrieval configuration, and retain comparison evidence. | Blocked | PLANNED ONLY — W10-002: Implement reranking, backend parity and retrieval load/cost proof. Plain-language analogy: a second librarian reorders only already-authorized books and must justify the added delay.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W10-003 | 3 | MUST | RAG evaluation | Implement RAG evaluation, safety regression and version governance. | Production claims require a live privacy-safe golden set and immutable evaluation identities. | Codex (approved source) + Owner (execute/approve) | 4 | W10-003 | EVAL-002,PRIV-003 | GAP-05 is addressed only after owner-executed evidence; until then status remains NOT RUN. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W10/W10-003.md | Restore exact known-good RAG configuration and block failed candidate identities. | Blocked | PLANNED ONLY — W10-003: Implement RAG evaluation, safety regression and version governance. Plain-language analogy: a crash-test and quality laboratory where every vehicle configuration is serialized before release.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W10-004 | 4 | MUST | AI operations | Extend existing AI observability with agent-step, retrieval, model, token, per-request cost, groundedness, citation, abstention, PII and authorization signals. | Operators must separate agent, retrieval and model behavior without logging sensitive payloads or rebuilding the telemetry stack. | Codex (approved source) + Owner (execute/approve) | 3.5 | W10-004 | OBS-002,RET-004 | Telemetry contracts and tests prove distinct retrieval/model latency, agent-step correlation, token and cost-per-request accounting, quality/safety signals, privacy, bounded cardinality, delivery alarms and retention. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W10/W10-004.md | Disable new exporters/logging, preserve safe evidence and retain existing telemetry path. | Blocked | PLANNED ONLY — W10-004. Extend existing AI observability with agent-step, retrieval, model, token, per-request cost, groundedness, citation, abstention, PII and authorization signals. Telemetry contracts and tests prove distinct retrieval/model latency, agent-step correlation, token and cost-per-request accounting, quality/safety signals, privacy, bounded cardinality, delivery alarms and retention. Main Prompt performs repository inspection; Column L/M require separate exact owner-approved manifests. Tracker v1.4.0 may remain open and owner-managed.
W10-LEARN-001 | 5 | MUST | Weekly learning | Complete the Week 10 advanced-RAG and LLMOps teach-back. | The owner must explain hybrid retrieval, reranking, evaluation and privacy-safe operations. | Codex (approved source) + Owner (execute/approve) | 1 | W10-LEARN-001 | None | Owner explains relevance, evaluation, drift, failure and cost trade-offs with five interview answers. | OWNER-CONTROLLED — complete task-specific teach-back after approved content and actual evidence; testing N/A only with reason. | docs/learning/W10-learning-review.md | Revise only through the approved documentation workflow. | Blocked | PLANNED ONLY — W10-LEARN-001: Complete the Week 10 advanced-RAG and LLMOps teach-back. Plain-language analogy: teaching a research desk that ranks authorized sources and continuously audits answer quality.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
Grouped prompt sequence — full Main / Code Edit / Document Writing / Final Approval prompts are in 10 Codex Prompts
Order | Prompt ID | Feature | Purpose | Required Inputs | Expected Outputs | Example Usage
1 | W10-001 | Hybrid retrieval | Implement hybrid retrieval by extending the existing OpenSearch adapter. | W7-001-remediation; W9-004 | Hybrid retrieval contract preserves authorization, citations and deterministic normalized results. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
2 | W10-002 | Reranking and parity | Implement reranking, backend parity and retrieval load/cost proof. | W7-001-remediation; W10-001 | Measured criteria govern reranker adoption; parity and authorization regressions fail closed. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
3 | W10-003 | RAG evaluation | Implement RAG evaluation, safety regression and version governance. | W7-001-remediation; W10-002 | GAP-05 is addressed only after owner-executed evidence; until then status remains NOT RUN. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
4 | W10-004 | AI operations | Extend existing AI observability with agent-step, retrieval, model, token, per-request cost, groundedness, citation, abstention, PII and authorization signals. | W7-001-remediation; W10-003 | Telemetry contracts and tests prove distinct retrieval/model latency, agent-step correlation, token and cost-per-request accounting, quality/safety signals, privacy, bounded cardinality, delivery alarms and retention. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
5 | W10-LEARN-001 | Weekly learning | Complete the Week 10 advanced-RAG and LLMOps teach-back. | W7-001-remediation; W10-004 | Owner explains relevance, evaluation, drift, failure and cost trade-offs with five interview answers. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update

## 23 W11 SRE and DR
Week 11 — SRE, Chaos Engineering and Disaster Recovery
SLOs, chaos, restore and incident operations deepen the existing SRE foundation.
Progress |  |  | Blocked |  |  | Exit gate
0% |  |  | 5 |  |  | All four implementation tasks require their own owner evidence. Deferred W6 P0 gaps do not alone block separately approved source-only Column L; they remain blockers for dependent live/cloud execution and final readiness/closure.
Step ID | Seq | Priority | Workstream | Action | Architecture Reason | Owner | Effort | Prompt | User TODO | Acceptance | Owner Verify | Evidence | Rollback/Teardown | Status | Task Context
W11-001 | 1 | MUST | AI reliability | Implement AI SLI/SLO and error-budget governance for reliability, retrieval quality, grounding, abstention, authorization, privacy, tokens and cost. | Release decisions need measurable user outcomes, including wrong retrieval, leakage and expensive success—not generic availability alone. | Codex (approved source) + Owner (execute/approve) | 3 | W11-001 | SLO-002,ALERT-001 | Definitions and tests cover citation coverage, retrieval relevance, grounded-answer rate, correct abstention, unauthorized retrieval rate, PII leakage rate, tokens and cost per successful query, each with denominator, window, threshold, sample and missing-data behavior. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W11/W11-001.md | Restore prior thresholds only through reviewed policy/runbook change. | Blocked | PLANNED ONLY — W11-001. Implement AI SLI/SLO and error-budget governance for reliability, retrieval quality, grounding, abstention, authorization, privacy, tokens and cost. Definitions and tests cover citation coverage, retrieval relevance, grounded-answer rate, correct abstention, unauthorized retrieval rate, PII leakage rate, tokens and cost per successful query, each with denominator, window, threshold, sample and missing-data behavior. Main Prompt performs repository inspection; Column L/M require separate exact owner-approved manifests. Tracker v1.4.0 may remain open and owner-managed.
W11-002 | 2 | MUST | Chaos engineering | Implement AWS FIS and controlled dependency-chaos framework. | Broader failures must be exercised with exact targets, stop alarms and bounded recovery objectives. | Codex (approved source) + Owner (execute/approve) | 3.5 | W11-002 | FIS-002,RES-002 | Exercises are designed and locally validated; live FIS remains NOT RUN until separately approved. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W11/W11-002.md | Stop exact experiment, restore dependencies/configuration, verify health and reconcile residue. | Blocked | PLANNED ONLY — W11-002: Implement AWS FIS and controlled dependency-chaos framework. Plain-language analogy: a fire drill with marked rooms, observers and an emergency stop—not setting the whole building alight.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W11-003 | 3 | MUST | Disaster recovery | Implement backup, restore, index rebuild and multi-Region DR contracts. | Rollback is not disaster recovery; state, data and indexes need independent recoverability. | Codex (approved source) + Owner (execute/approve) | 4 | W11-003 | DR-001,RPO-001 | Recovery plans bind exact identities and distinguish backup, restore, rebuild, rollback and teardown. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W11/W11-003.md | Abort restore on identity or scope mismatch; preserve original state and recovery evidence. | Blocked | PLANNED ONLY — W11-003: Implement backup, restore, index rebuild and multi-Region DR contracts. Plain-language analogy: rebuilding a library from a verified archive while checking every catalog and access record.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W11-004 | 4 | MUST | Incident operations | Implement incident management, game days, runbooks, failure-proof runners and identity-bound recovery evidence. | Operators need accountable response and proof that recovery achieved the required RTO/RPO, not only a runbook. | Codex (approved source) + Owner (execute/approve) | 4 | W11-004 | INC-001,OPS-001 | Offline and owner-run evidence records exact scenario and identities, approvals, commands/workflows, achieved-versus-target RTO/RPO, integrity/health, cleanup and residual risk; any failed command prevents PASS. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W11/W11-004.md | Disable defective runner/playbook, retain failed evidence and return to last validated runbook. | Blocked | PLANNED ONLY — W11-004. Implement incident management, game days, runbooks, failure-proof runners and identity-bound recovery evidence. Offline and owner-run evidence records exact scenario and identities, approvals, commands/workflows, achieved-versus-target RTO/RPO, integrity/health, cleanup and residual risk; any failed command prevents PASS. Main Prompt performs repository inspection; Column L/M require separate exact owner-approved manifests. Tracker v1.4.0 may remain open and owner-managed.
W11-LEARN-001 | 5 | MUST | Weekly learning | Complete the Week 11 SRE, chaos and DR teach-back. | The owner must distinguish availability, resilience, rollback, restore and disaster recovery. | Codex (approved source) + Owner (execute/approve) | 1 | W11-LEARN-001 | None | Owner explains SLOs, error budgets, chaos safety, RPO/RTO and incident response with five interview answers. | OWNER-CONTROLLED — complete task-specific teach-back after approved content and actual evidence; testing N/A only with reason. | docs/learning/W11-learning-review.md | Revise only through the approved documentation workflow. | Blocked | PLANNED ONLY — W11-LEARN-001: Complete the Week 11 SRE, chaos and DR teach-back. Plain-language analogy: teaching emergency preparedness from alarms through drills, recovery and after-action review.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
Grouped prompt sequence — full Main / Code Edit / Document Writing / Final Approval prompts are in 10 Codex Prompts
Order | Prompt ID | Feature | Purpose | Required Inputs | Expected Outputs | Example Usage
1 | W11-001 | AI reliability | Implement AI SLI/SLO and error-budget governance for reliability, retrieval quality, grounding, abstention, authorization, privacy, tokens and cost. | W7-001-remediation; W10-004 | Definitions and tests cover citation coverage, retrieval relevance, grounded-answer rate, correct abstention, unauthorized retrieval rate, PII leakage rate, tokens and cost per successful query, each with denominator, window, threshold, sample and missing-data behavior. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
2 | W11-002 | Chaos engineering | Implement AWS FIS and controlled dependency-chaos framework. | W7-001-remediation; W11-001 | Exercises are designed and locally validated; live FIS remains NOT RUN until separately approved. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
3 | W11-003 | Disaster recovery | Implement backup, restore, index rebuild and multi-Region DR contracts. | W7-001-remediation; W11-002 | Recovery plans bind exact identities and distinguish backup, restore, rebuild, rollback and teardown. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
4 | W11-004 | Incident operations | Implement incident management, game days, runbooks, failure-proof runners and identity-bound recovery evidence. | W7-001-remediation; W11-003 | Offline and owner-run evidence records exact scenario and identities, approvals, commands/workflows, achieved-versus-target RTO/RPO, integrity/health, cleanup and residual risk; any failed command prevents PASS. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
5 | W11-LEARN-001 | Weekly learning | Complete the Week 11 SRE, chaos and DR teach-back. | W7-001-remediation; W11-004 | Owner explains SLOs, error budgets, chaos safety, RPO/RTO and incident response with five interview answers. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update

## 24 W12 Capstone
Week 12 — Enterprise AI Architect Capstone and Automated Closure
Owner-approved GitHub Actions and HCP Terraform/Terraform Cloud workflows automate deployment, rollback and teardown.
Progress |  |  | Blocked |  |  | Exit gate
0% |  |  | 5 |  |  | All four implementation tasks require their own owner evidence. Deferred W6 P0 gaps do not alone block separately approved source-only Column L; they remain blockers for dependent live/cloud execution and final readiness/closure.
Step ID | Seq | Priority | Workstream | Action | Architecture Reason | Owner | Effort | Prompt | User TODO | Acceptance | Owner Verify | Evidence | Rollback/Teardown | Status | Task Context
W12-001 | 1 | MUST | Automated deployment | Integrate the capstone and automate end-to-end deployment through GitHub Actions and HCP Terraform/Terraform Cloud. | The final operating model must execute approved immutable plans without ad-hoc manual deployment. | Codex (approved source) + Owner (execute/approve) | 4 | W12-001 | GHA-003,TFC-001,PROD-001 | Workflow design preserves explicit owner approval and exact-plan binding; live execution remains separately approved. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W12/W12-001.md | Freeze workflow, preserve run evidence and invoke only the separately approved rollback workflow. | Blocked | PLANNED ONLY — W12-001: Integrate the capstone and automate end-to-end deployment through GitHub Actions and HCP Terraform/Terraform Cloud. Plain-language analogy: a sealed automated assembly line that runs only the signed work order approved by inspectors.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W12-002 | 2 | MUST | Automated recovery | Automate application/infrastructure rollback and validate DR recovery. | Recovery must restore exact known-good identities without manual intervention disguised as automation. | Codex (approved source) + Owner (execute/approve) | 4 | W12-002 | ROLLBACK-002,DR-002 | Application rollback, infrastructure rollback and DR remain separate, identity-bound automated workflows. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W12/W12-002.md | Stop automation, preserve partial state, reconcile read-only and resume only with fresh approval. | Blocked | PLANNED ONLY — W12-002: Automate application/infrastructure rollback and validate DR recovery. Plain-language analogy: three labeled emergency procedures, each with its own key, checklist and verification.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W12-003 | 3 | MUST | Automated teardown | Automate teardown, resource cleanliness and cost closure. | A disposable platform is complete only when approved automation proves native absence and billing closure. | Codex (approved source) + Owner (execute/approve) | 4 | W12-003 | DEST-003,COST-008,KMS-003 | Automated workflow preserves exact approval, ordered teardown, native absence and delayed cost evidence. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W12/W12-003.md | Deletion is not rolled back; stop before uncertain targets and restore only from approved backups where supported. | Blocked | PLANNED ONLY — W12-003: Automate teardown, resource cleanliness and cost closure. Plain-language analogy: closing a facility room by room with an inventory, archive and final utility bills.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
W12-004 | 4 | MUST | Governance closure | Prepare the final governance, production-readiness, threat-model and portfolio closure package. | Final readiness must reconcile technical evidence and current attack paths, not infer production status from implementation. | Codex (approved source) + Owner (execute/approve) | 4 | W12-004 | PROD-002,DOC-001 | The package explicitly covers architecture, threat model with accepted/unresolved attack paths, readiness, automated deployment/rollback, DR, teardown, cost, lineage, evaluation/load, dashboards, runbooks and portfolio outputs while preserving every pending or qualified gate. | OWNER-CONTROLLED — after exact Column L edits, Codex supplies copy-ready commands in the verified shell: focused tests → full configured quality/security/policy regression → evidence/residue checks; one at a time with stop conditions. Live/cloud work needs separate approval. | docs/test-evidence/W12/W12-004.md | Withdraw readiness claim, preserve package, and reopen exact failed or missing gates. | Blocked | PLANNED ONLY — W12-004. Prepare the final governance, production-readiness, threat-model and portfolio closure package. The package explicitly covers architecture, threat model with accepted/unresolved attack paths, readiness, automated deployment/rollback, DR, teardown, cost, lineage, evaluation/load, dashboards, runbooks and portfolio outputs while preserving every pending or qualified gate. Main Prompt performs repository inspection; Column L/M require separate exact owner-approved manifests. Tracker v1.4.0 may remain open and owner-managed.
W12-LEARN-001 | 5 | MUST | Weekly learning | Complete the Week 12 capstone and Principal/Architect teach-back. | The owner must present the entire platform as a governed business, architecture and operations story. | Codex (approved source) + Owner (execute/approve) | 1.5 | W12-LEARN-001 | None | Owner delivers an interview-ready end-to-end narrative and answers architecture, security, SRE, cost and governance follow-ups. | OWNER-CONTROLLED — complete task-specific teach-back after approved content and actual evidence; testing N/A only with reason. | docs/learning/W12-learning-review.md | Revise only through the approved documentation workflow. | Blocked | PLANNED ONLY — W12-LEARN-001: Complete the Week 12 capstone and Principal/Architect teach-back. Plain-language analogy: teaching an audited launch sequence from signed plan through recovery and final site closure.. After Column L, explain the real component flow, security/failure and trade-offs, then give exact owner TEST-001 commands; results remain NOT RUN until executed. Tracker v1.4.0 may stay open and owner-managed.
Grouped prompt sequence — full Main / Code Edit / Document Writing / Final Approval prompts are in 10 Codex Prompts
Order | Prompt ID | Feature | Purpose | Required Inputs | Expected Outputs | Example Usage
1 | W12-001 | Automated deployment | Integrate the capstone and automate end-to-end deployment through GitHub Actions and HCP Terraform/Terraform Cloud. | W7-001-remediation; W11-004 | Workflow design preserves explicit owner approval and exact-plan binding; live execution remains separately approved. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
2 | W12-002 | Automated recovery | Automate application/infrastructure rollback and validate DR recovery. | W7-001-remediation; W12-001 | Application rollback, infrastructure rollback and DR remain separate, identity-bound automated workflows. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
3 | W12-003 | Automated teardown | Automate teardown, resource cleanliness and cost closure. | W7-001-remediation; W12-002 | Automated workflow preserves exact approval, ordered teardown, native absence and delayed cost evidence. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
4 | W12-004 | Governance closure | Prepare the final governance, production-readiness, threat-model and portfolio closure package. | W7-001-remediation; W12-003 | The package explicitly covers architecture, threat model with accepted/unresolved attack paths, readiness, automated deployment/rollback, DR, teardown, cost, lineage, evaluation/load, dashboards, runbooks and portfolio outputs while preserving every pending or qualified gate. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update
5 | W12-LEARN-001 | Weekly learning | Complete the Week 12 capstone and Principal/Architect teach-back. | W7-001-remediation; W12-004 | Owner delivers an interview-ready end-to-end narrative and answers architecture, security, SRE, cost and governance follow-ups. | Review Main Prompt → exact edit approval → owner testing → documentation approval → final owner approval and tracker update